## Project Management Plan
Week | Task | Difficult
2023-07-02 | Create a repo in github | Easy
| Create a project plan | Easy
| Create trello broad and estimate task in plan | Easy
| Set Up Azure Account | Easy
2023-07-09 | Set Up Azure Cloud Shell | Easy
| Configure GitHub Actions | Medium
| Test GitHub Actions in branch test-git-action | Easy
| Replace the scaffolding code with the flask code | Easy
| Test flask code in local | Easy
2023-07-16 | Create Virtual Machine | Easy
| Set Up Azure Pipeline | Hard
| Deploy an application using Azure Pipelines into Azure App Services | Medium
| Inspect the logs from running application | Easy
| Making predictions | Easy
| Load test an application using Locust | Easy
2023-07-23 | Create a Document in Readme | Medium
| Create a Demo video | Medium
| Review and Fix Bug | Easy
| Goals | Successfully build a CI/CD Pipeline and deploy web application by using CI/CD
2023 Quater 3 Plan | Successfully demo & get approval from team to apply this CI/CD
Yearly Plan | Apply this solution to deploy Application